## Sprint2Delivedrables
Date | 2017-03-20
Project | Facer
Sprint | 2
Team | Deliverables | Status | Scheduled Start Date | Actual Start Date | Scheduled End Date | Actual End Date | Note
Client | API Diagrem | Not-Started | 2017-03-21 |  | 2017-03-21
Server | Webservice and StandartTables (App,Comp,Users,User) | Not-Started | 2017-03-21 |  | 2017-03-23
Server | Webservices (App,Comp,Users,User) | Not-Started | 2017-03-21 |  | 2017-03-23
Server | User Autentication | Not-Started | 2017-03-21 |  | 2017-03-23
Server | Server Event Tables | Not-Started | 2017-03-21 |  | 2017-03-23
Server | Backend webservice to populate data into Summary Tables (App,Comp,Users,User) | Not-Started | 2017-03-21 |  | 2017-03-23