## Plan
Date | 2017-03-20
Project | Facer
Sprint | 2
Team | Task | Priority | Owner | Status | Scheduled Start Date | Actual Start Date | Scheduled End Date | Actual End Date | Note
Server | Finilize Sprint 2 API | High | Joe,Jay,Raghu,Greg,Ivan | Not-Started | 2017-03-21 |  | 2017-03-21
Client | Modify API Diagram | High | Raghu | Not-Started | 2017-03-21 |  | 2017-03-21
Server | Create database script for Sprint2 | High | Angel | Not-Started | 2017-03-21 |  | 2017-03-23
Server | Create table, entity & DAO classes, - Applications | High | Bob | Not-Started | 2017-03-21 |  | 2017-03-23
Server | Create table,entity & DAO classes - Components | High | Brian | Not-Started | 2017-03-21 |  | 2017-03-23
Server | Create table,entity & DAO classes - Incidents | High | DeAnthony | Not-Started | 2017-03-21 |  | 2017-03-23
Server | Add References to Facer resource file | High | DeAnthony | Not-Started | 2017-03-21 |  | 2017-03-23
Server | Finilize Sprint 2 standard tables | High | Greg,Ivan | Not-Started | 2017-03-22 |  | 2017-03-22
Server | Review Sprint 2 db scripts | High | Greg,Ivan | Not-Started | 2017-03-22 |  | 2017-03-22
Server | Design and Implement authentication function - All webservices | High | Greg,Ivan |  | 2017-03-21 |  | 2017-03-23
Server | Design Event Tables | Low | Greg,Ivan | Not-Started | 2017-03-21 |  | 2017-03-23
Server | Create table,entity & DAO classes -Event | Low | Greg,Ivan | Not-Started | 2017-03-21 |  | 2017-03-23 | Server Events
Server | Create table,entity & DAO classes -Std Tables | Low | Greg,Ivan | Not-Started | 2017-03-21 |  | 2017-03-23
Server | Design Backend webservice to populate data into Summary Tables (App,Comp,Users,User) | Low | Greg,Ivan | Not-Started | 2017-03-21 |  | 2017-03-23